## Risk register
ID | Risk | Source / scenario | Asset | Threat | Vulnerability | L (1-5) | I (1-5) | Inherent score | Inherent level | Existing controls | Evidence of effectiveness (measured) | Residual L | Residual I | Residual score | Residual level | Treatment | Planned action | Owner | Target | Status | ISO 27001:2022 Annex A | CIS AWS 7.0 section
R01 | Customer data exposed publicly through an S3 misconfiguration | S1 | S3 data bucket (PII) | Anonymous internet user | Bucket-level BPA can be disabled; no account-level BPA, no SCP | 4 | 5 | 20 | High | Bucket BPA + TLS-only policy; SSE-KMS copy; Wazuh 100100-104; Lambda L1 auto re-block | S1a: detected 3 min 34 s after the read, manual fix 7 min 55 s; S1b-2: L1 fixed in 9.9 s; KMS copy never readable | 2 | 4 | 8 | Medium | Mitigate | Account-level S3 BPA (done 2026-10-25, CIS 3.1.4 pass); L1 should also remove the public policy statement | Ziad A. | 2026-10-25 | Closed | 5.15, 5.23, 8.3, 8.12, 8.24 | 3 Storage
R02 | Long-lived CI access key leaked through source code | S2 | dev-ci IAM user, data bucket | External attacker / secret-scanning bots | Static key stored in a file in Git history; no secret scanning | 4 | 4 | 16 | High | Least-privilege dev-ci (no kms:Decrypt); Wazuh 100110 (unknown IP); RB-S2 runbook | Detected 3 min 41 s after first misuse; contained 2 min 42 s after alert; KMS copy denied | 3 | 3 | 9 | Medium | Mitigate | OIDC federation for CI (no standing keys); pre-commit + push-protection secret scanning | Ziad A. | Recommended | Open | 5.17, 8.4, 8.5, 8.28 | 2 IAM
R03 | Attacker persistence through additional access keys | S2 | IAM users | Attacker holding a valid key | Identity allowed to create its own keys | 3 | 4 | 12 | Medium | Wazuh 100113 (level 14) via us-east-1 IAM poller; AWSDenyAll-first containment | Persistence detected 3 min 40 s after creation; neutralized 5 min 21 s after creation | 2 | 3 | 6 | Low | Mitigate | Remove iam:CreateAccessKey from CI identities | Ziad A. | Recommended | Open | 5.16, 5.18, 8.2 | 2 IAM
R04 | Administrative port exposed to the internet and attacked | S3 | EC2 web instance | Internet scanners, brute force | Security group can be opened to 0.0.0.0/0; no NACL second layer | 4 | 4 | 16 | High | No key pair, no password auth, SSM only; Wazuh 100121 + 5710/5712; Lambda L2 | Hydra aborted (no password auth); S3a manual 7 min 57 s; S3b L2 5.3 s; agent detection in seconds | 2 | 2 | 4 | Low | Mitigate | NACL + VPC flow logs done 2026-10-25 (CIS 4.7 pass); 100121+57xx correlation recommended | Ziad A. | 2026-10-25 | Closed | 8.20, 8.22, 8.5, 8.16 | 6 Networking
R05 | Instance role credentials stolen through IMDSv1 + SSRF | M-IMDS | lab-web-role credentials | Attacker exploiting a web SSRF | IMDSv1 can be re-enabled per instance | 3 | 4 | 12 | Medium | IMDSv2 required, hop limit 1; Lambda L3; Wazuh 100132; rules 100130/131/133 for credential use outside the instance | L3 fixed in 6.4 s; 100132 in 1 min 23 s | 1 | 4 | 4 | Low | Mitigate | Account default IMDSv2 required (done 2026-10-25) | Ziad A. | 2026-10-25 | Closed | 8.9, 8.20 | 6 Networking
R06 | Automated remediation silently not working | S1b-1 | Lambda L1-L3 / EventBridge | Operational failure | Rule changes and new trails are eventually consistent; no health check of automation | 3 | 4 | 12 | Medium | SIEM detection independent of automation; session checklist (wait ≥ 60 s / ≥ 5 min) | S1b-1: L1 never ran, Wazuh still alerted ~1 min after first read; bucket public 6 min 25 s | 2 | 3 | 6 | Low | Mitigate | Keep rules always on; canary test after changes; alert if 100101 not followed by an L1 confirmation within 2 min | Ziad A. | Phase 5 | Open | 8.16, 5.30 | 5 Monitoring
R07 | IAM activity missed by the regional trail | Phase 1 finding | Detection pipeline | Any IAM misuse | IAM is global and logged only in us-east-1; Free plan has no multi-region trail | 4 | 4 | 16 | High | IAM poller on the us-east-1 event history (every 2 min) | 100111/100113 fired live on IAM events; latency 2.5-4 min | 2 | 3 | 6 | Low | Accept (compensated) | Multi-region trail when the plan allows it | Ziad A. | — | Accepted | 8.15, 8.16 | 4 Logging
R08 | Late CloudTrail files skipped by log ingestion | Phase 2 finding | Detection pipeline | Any attack in data events | Polling reader tracked the last file name; data-event files arrive out of order | 4 | 4 | 16 | High | S3 → SQS notification + reader in arrival order, DLQ, de-dup | All 26 anonymous reads in S1 ingested (100103); 0 lost | 1 | 3 | 3 | Low | Mitigate | — | Ziad A. | Done | Closed | 8.15, 8.16 | 4 Logging
R09 | Activity in other regions not monitored | Design | AWS account | Attacker using an unused region | Single-region trail (multi-region unsupported on the plan); rule 100151 cannot fire | 2 | 3 | 6 | Low | Account restricted to one region by the plan itself | — | 2 | 2 | 4 | Low | Accept | Re-assess if the plan changes | Ziad A. | — | Accepted | 8.15, 8.16 | 4 Logging
R10 | Over-privileged admin IAM user with a long-lived key | Phase 0 | Whole account | Key theft from the laptop | AdministratorAccess on a user with a CLI key | 3 | 5 | 15 | High | MFA on console, key only on the laptop, budget alert, own-admin activity logged (100143), password policy (CIS 2.8/2.9) | Hardening attempt showed groups are denied by the account SCP | 2 | 5 | 10 | Medium | Accept (temporary) | Groups blocked by an AWS-managed SCP (explicit deny on iam:CreateGroup, 2026-10-25); delete the key at Phase 6 | Ziad A. | Phase 6 | Accepted | 5.15, 5.18, 8.2 | 2 IAM
R11 | Tailscale auth key exposed in a chat | Phase 2 | Tailnet (SIEM network) | Anyone who saw the key | Reusable key, not rotated by decision | 2 | 3 | 6 | Low | Ephemeral nodes; Tailscale Machines list checked after sessions | No unknown device seen | 2 | 3 | 6 | Low | Accept (temporary) | Revoke the key at the end of the lab; Tailscale ACL | Ziad A. | Phase 6 | Accepted | 5.17, 8.5 | —
R12 | Instance role can read the Tailscale key and join the SIEM network | Design | Tailnet, Wazuh manager | Attacker with the role's credentials | Role allowed ssm:GetParameter on the auth key; no tailnet ACL | 2 | 4 | 8 | Medium | IMDSv2 + L3 (credential theft hard); Wazuh 100130 for role use outside the instance | — | 2 | 3 | 6 | Low | Mitigate | Tagged auth key + ACL limiting EC2 to Wazuh ports 1514/1515 | Ziad A. | Phase 5 | Open | 8.20, 8.22, 5.15 | —
R13 | Dynamic home IP breaks IP-pinned controls / creates false positives | Operations | wazuh-reader policy, known-IP list | — | ISP changes the IP almost daily | 4 | 2 | 8 | Medium | refresh_home_ip.ps1 at the start of each session | 100150 false positives seen for the previous day's IP | 3 | 1 | 3 | Low | Accept | Fixed IP or VPN egress in a real deployment | Ziad A. | — | Accepted | 8.16 | —
R14 | No managed threat detection (GuardDuty, Security Hub, Config) | Plan limitation | AWS account | Threats outside custom rules | Services not available on the account's plan | 4 | 3 | 12 | Medium | 21 custom Wazuh rules; Prowler CIS scans; 15 CIS CloudWatch-alarm checks compensated by Wazuh rules | Every scenario detected by at least one rule | 3 | 2 | 6 | Low | Accept (compensated) | Enable GuardDuty/Security Hub/Config when the plan allows it | Ziad A. | — | Accepted | 5.7, 8.16 | 5 Monitoring
R15 | Sensitive identifiers published in the public repository | Phase 6 prep | GitHub repo | Anyone reading the repo | Binary files not covered by text scans; key IDs decode to the account ID | 3 | 3 | 9 | Medium | History purges (tfplan, run log), account ID placeholders, TruffleHog before publishing | Fresh-clone scan: no key ID, IP or account ID in any commit | 1 | 2 | 2 | Low | Mitigate | Unzip-and-grep binaries before each commit | Ziad A. | Done | Closed | 5.12, 5.13, 8.12 | —
R16 | Detection slower than data theft | All scenarios | Data bucket | Fast attacker | CloudTrail delivery takes minutes; exfiltration takes seconds | 4 | 4 | 16 | High | Automated containment (5-10 s); preventive controls (KMS, least privilege) | Data read within seconds of T0 in S1/S2; detection 1-4 min | 3 | 3 | 9 | Medium | Mitigate | Favour preventive controls (account BPA, OIDC, no standing keys) | Ziad A. | Phase 5 | Open | 8.16, 5.26 | 5 Monitoring
R17 | SIEM single point of failure | Design | Wazuh VM | Laptop failure, disk issues | One all-in-one VM, no HA, no snapshots | 3 | 3 | 9 | Medium | Offline VM backups to external HDD; SQS buffers trail events (4 days) | VM down → events wait in SQS, no loss | 2 | 3 | 6 | Low | Accept | — | Ziad A. | — | Accepted | 5.30, 8.13 | —

## Summary
Risk register summary
| Inherent | Residual
Risks rated High | 7 | 0
Risks rated Medium | 8 | 4
Risks rated Low | 2 | 13
Total risks | 17
Average score | 12.3 | 5.8
Status: Open | 5
Status: In progress | 0
Status: Accepted | 7
Status: Closed | 5

## Method
Method | Qualitative 5×5 matrix (ISO/IEC 27005 style). Score = Likelihood × Impact.
Likelihood (L) | 1 rare · 2 unlikely · 3 possible · 4 likely · 5 almost certain (within a year, for a small company running this setup).
Impact (I) | 1 negligible · 2 minor · 3 moderate · 4 major (PII exposure, account compromise) · 5 severe (full account takeover, large PII breach).
Levels | High ≥ 15 · Medium 8–14 · Low ≤ 7.
Inherent vs residual | Inherent = before the lab's controls. Residual = with the controls in place, using the measured results from the 2026-10-24 runs as evidence.
Treatment | Mitigate (add/strengthen controls) · Accept (documented, owner aware) · Transfer · Avoid.
Yellow cells | Inputs to adjust (L, I, residual L/I, status). Scores and levels are formulas.
Sources | Incident reports in reports/incidents/, run log reports/timelines.xlsx, Prowler CIS AWS 7.0 scans, kickoff brief.